## Sheet1
project | phase | phase_window | schedule_delay_months | eii_cost_overrun_pct | eii_financing_disruption_freq | eii_contractor_claims_vol | sii_vader_mean_compound | sii_sentiment_impact_inverted | sii_displacement_events | enii_incident_density | enii_sedimentation_events | enii_landuse_conflicts | enii_compliance_failures | EII_composite | SII_composite | EnII_composite | igq_coder1 | igq_coder2 | igq_final | source_doc_ids | schedule_delay_derivation_notes | eii_notes | sii_notes | enii_notes | igq_numeric_1to5
PMBP | 1 | 2012-2015 | 0 | 101.9 | 1 | 0 | 0.3961 | -0.3961 | 0 | 1 | 0 | 0 | 0 | 0.487 | 0.378 | 0.125 | Low | Low | Low | PMBP_NEWS_007; PMBP_INST_001 | Baseline reference point. Original ECNEC-approved target (Aug 2007) was June 2015 (per PMBP_NEWS_007, corroborated by external TBS reporting). Phase 1 window (2012-2015) ends at this original target date by design, so delay=0 here is the zero-point the rest of the series is measured against, not a claim that nothing had gone wrong yet. | Cost: Tk101.61bn (2007 ECNEC) -> Tk205.07bn (2011 revision, post-redesign) = 101.9% overrun vs original. Financing disruption: World Bank's 2012 IDA credit cancellation forcing self-financing shift (1 major event). Contractor claims: none documented pre-construction (construction hadn't started). | REVISED 2026-09-18: PMBP_NEWS_059 ('Govt Rehabilitates the Displaced', 11 Dec 2015) was corrected in the corpus index from Phase 1 to Phase 2 (falls inside the 2015-2019 window, not 2012-2015). Its displacement-event contribution moves with it - corrected from 1 to 0 here. No other displacement/interruption evidence exists for PMBP Phase 1. vader fields blank pending full-text corpus. | REVISED 2026-09-18: land-use conflict contribution from PMBP_NEWS_059 (agricultural landowner compensation complaints) moves to Phase 2 following its corpus-index phase correction. Corrected from 1 to 0 here. Incident density (1, justified independently by the 2011 design redesign) and other components are unaffected. | 1
PMBP | 2 | 2015-2019 | 72 | 183.4 | 0 | 0 | 0.2263 | -0.2263 | 2 | 1 | 1 | 2 | 0 | 0.277 | 0.991 | 0.625 | Low-Moderate | Low-Moderate | Low-Moderate | PMBP_NEWS_013; PMBP_NEWS_060; PMBP_NEWS_014; PMBP_NEWS_063; PMBP_NEWS_059 | Cumulative delay vs. June 2015 baseline. By end of Phase 2 (Dec 2019), the documented target had been revised to June 2021 (PMBP_NEWS_013, 'Padma Bridge gets 18th span'). June 2015 -> June 2021 = 72 months. | Cost: Tk101.61bn baseline -> Tk287.93bn (Jan 2016 2nd DPP revision) = 183.4% overrun. No further revision through 2019. Financing disruption: Dec 2019 emergency RADP fund request for the Dhaka-Mawa expressway, with documented Planning Commission/RHD friction (PMBP_NEWS_014) - NOTE this document is scope-flagged (see Shahriar's evidence pack cross-cutting issue 2, expressway vs. bridge boundary); counted here provisionally, flag if scope is narrowed. Contractor claims: none documented in this phase. | REVISED 2026-09-18: PMBP_NEWS_059's displacement event (70% of 3,000 displaced residents relocated, Dec 2015) now counted here following its corpus-index phase correction (Phase 1 -> Phase 2). This is a distinct event from the already-counted Naria erosion (PMBP_NEWS_063, 2018) - different trigger, different mechanism - so it adds as a second event (1 -> 2) rather than merging under the combined-cluster convention, which applies only to follow-on actions from one shared trigger. vader fields blank pending full-text corpus. | REVISED 2026-09-18: PMBP_NEWS_059's land-use conflict (agricultural landowner compensation complaints) now counted here following its phase correction. Distinct trigger from the already-counted khas-to-private reclassification dispute (PMBP_NEWS_062), so adds as a second event (1 -> 2). Incident density (1, NASA historical finding) and sedimentation (1, dredge-spoil disposal) are unaffected. | 2
PMBP | 3 | 2019-2022 | 84 | 197.2 | 1 | 1 | 0.3113 | -0.3113 | 1 | 2 | 0 | 0 | 1 | 0.964 | 0.685 | 0.5 | Low-Moderate | Moderate-High | Moderate-High | PMBP_NEWS_021; PMBP_NEWS_021; PMBP_NEWS_066; PMBP_NEWS_005; PMBP_NEWS_070; PMBP_NEWS_037; PMBP_NEWS_038; PMBP_NEWS_071 | Cumulative delay vs. June 2015 baseline. Actual opening 25 June 2022. June 2015 -> June 2022 = 84 months. Matches the Chapter 1-3 locked figure exactly. | Cost: Tk101.61bn baseline -> Tk301.93bn (2018 revision, held through the Jun 2022 opening) = 197.2% overrun. Financing disruption: ADP allocation reduced to Tk2,099.93cr following the 2020-21 river-current stoppage (PMBP_NEWS_066) - 1 event. Contractor claims: contractor idle-equipment claims from the 2020-21 stoppage period, per PMBP_NEWS_005 (now correctly dated Oct 2020) - 1 event. | No new displacement events, but 4 documented service-interruption events count under this component per the codebook (SII component = 'displacement/service interruption events', combined): (1) ferry service suspensions after pier collisions, (2) BIWTC crew suspension, (3) ferry terminal relocation Shimulia->Paturia, (4) heavy-vehicle ban on the ferry route. All from the same Jul-Aug 2021 cluster; counted as 4 distinct regulatory/operational interruption events rather than 1, since each is a separately dated, separately targeted action. Flag for coder: could reasonably be counted as 1 cluster instead of 4 discrete events - this is a judgment call worth settling once and applying consistently to any similar cluster elsewhere. vader fields blank pending full-text corpus. | Incident density: 2 - (1) the 2020-21 four-month river-current stoppage, (2) the Jul-Aug 2021 ferry-pier collision cluster (grouped as one incident-type here, distinct from the 4-event SII service-interruption count, since this component measures ecological/hydrological incident occurrence rather than regulatory response count). Sedimentation: 0 in this phase specifically (no new dredging/sediment event beyond the ongoing river-training background). Land-use conflicts: 2 - Rail Link alignment requiring 100 additional private acres, and the Dhirasram ICD's 222-acre acquisition. Compliance failures: 1 - BIWTC's documented failure to act on ferry masters' prior written warnings before the collision cluster worsened - a genuine institutional/regulatory compliance failure, though it falls on ferry safety governance rather than EIA/DoE oversight of the bridge itself; flagged given the same regulatory-scope question raised in the Social/Environmental pathway analysis. | 4
PMBP | 4 | 2022-2026 | 84 | 220.9 | 1 | 1 | 0.3834 | -0.3834 | 0 | 1 | 1 | 2 | 1 | 1 | 0.387 | 0.875 | Moderate | Moderate | Moderate | PMBP_NEWS_007; PMBP_NEWS_048; PMBP_NEWS_078; PMBP_NEWS_049 | Carried forward unchanged: no further schedule slippage occurred post-opening. The 30 June 2024 defect-liability closeout is an administrative/contractual milestone, not a schedule delay. | Cost: Tk101.61bn baseline -> Tk326.06bn (Apr 2023 3rd ECNEC revision, PMBP_NEWS_007, cross-validated against external search) = 220.9% overrun. NOTE: Prothom Alo (PMBP_NEWS_047) separately cites Tk328.75bn for what appears to be an earlier-stage estimate of the same revision episode - used the Daily Star ECNEC-approved figure as authoritative since it's described as the actual approved amount. Financing disruption: Jun 2023 Tk1,117.97cr additional VAT-driven contractor payment (PMBP_NEWS_048) - 1 event. Contractor claims: same PMBP_NEWS_048 payment, framed by the source as settling contractor dues/VAT claims - 1 event (same underlying episode as the financing-disruption count; not double-counting two different real events, just two facets of one). | 0 new displacement events in this phase. The Shibchar compensation-fraud finding and the 2025 char-land purchase are retrospective accounts of Phase 2/3 acquisition conduct (per Shahriar's evidence pack, cross-cutting note on phase boundaries) rather than new Phase 4 events - consistent with leaving this at 0 rather than double counting evidence already attributed to earlier phases. vader fields blank pending full-text corpus. | Incident density: 1 - the 2023 unplanned upstream dredging threat to pier scour protection. Sedimentation: 1 - same dredging event, counted again here since it is specifically a sedimentation/scour-management issue (components capture distinct facets of one event where applicable). Land-use conflicts: 2 - the Shibchar compensation-fraud finding (PMBP_NEWS_078) and the 2025 politically-pressured char-land purchase (PMBP_NEWS_049). RESOLVED 2026-09-18: both are counted under Phase 4 by publication/discovery date, per the same publication-date convention applied to the corpus index generally - consistent with how these two documents are already dated Phase 4 there, even though the underlying land-acquisition conduct they describe occurred during earlier construction phases. Chapter 4 narrative should describe these explicitly as retrospective findings *published* in Phase 4, not conduct that occurred in Phase 4. Compliance failures: 1 - the unimplemented EIA-mandated wildlife sanctuary, unresolved two years post-opening. | 3
DMRP | 1 | 2012-2019 | 0 | 0 | 0 | 0 | 0.9638 | -0.9638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Moderate | High | High | DMRP_INST_007 | Baseline reference point. Per DMTCL's own progress report (DMRP_INST_007), the revised works-plan target for the Uttara-Agargaon (first) section was December 2019. Phase 1 window (2012-2019) ends at this original target date by design, matching the PMBP treatment. | Cost: no revision documented before 2019 end; still at the original Dec 2012 approved Tk219.85bn = 0% overrun. Financing disruption: none documented in this window. Contractor claims: none documented (construction had barely started). | 0 documented events - no displacement or service-interruption content found for this phase. vader fields blank pending full-text corpus. | No environmental incidents, sedimentation events, land-use conflicts, or compliance failures documented for this phase - DMRP is an elevated urban rail project with no river/sedimentation dimension at all, so zeroes here (especially sedimentation, structurally, across all DMRP phases) reflect the project type, not a coverage gap. | 5
DMRP | 2 | 2019-2022 | 36 | 0 | 0 | 0 | 0.6651 | -0.6651 | 0 | 0 | 0 | 0 | 1 | 0 | 0.199 | 0.25 | Moderate | Moderate-High | Moderate-High | DMRP_INST_007; DMRP_NEWS_014; DMRP_NEWS_009; DMRP_NEWS_016 | By the end of Phase 2 (mid-2022), the Dec 2022 opening date for the first section was already effectively fixed (government messaging from early 2021 pointed to a partial opening in this window). Dec 2019 -> Dec 2022 = 36 months, representing the delay already realized/locked in by this point. This resolves Ch.1-3's cited '36-48 months at the Phase 2 endpoint' to a specific figure using the first-section benchmark, per project decision. | Cost: the 52.25% cost escalation was announced 17 Jul 2022, after this phase's mid-2022 cutoff (see Shahriar's cross-cutting issue 3 on the DMRP Phase 2/3 boundary rule) - so at the strict Phase 2 endpoint (30 Jun 2022), the approved cost was still the original Tk219.85bn = 0% overrun. This is a real, notable finding: DMRP's cost escalation lagged its schedule escalation, unlike PMBP where both moved together from Phase 2 onward. If the group resolves the boundary question to reassign the escalation announcement into Phase 2, this value would need to change to 52.25% - flagging that dependency explicitly. Financing disruption: the 2019 JICA loan-tranche signing friction ('Japan softens stance', DMRP_NEWS_009) is a borderline financing-friction event, but resolved without a stated disruption to progress - counted as 0, noted as borderline. Contractor claims: none documented for DMRP in any phase in the current corpus - itself a notable structural gap, likely institutional-source-dependent. | 0 documented events - consistent with the Social pathway's own finding of a genuine evidence gap for DMRP Phase 2 (not a considered absence, an uncovered one). vader fields blank pending full-text corpus. | Incident density: 0 (the air-quality violation is counted under compliance_failures, not double-counted here as a separate ecological incident). Sedimentation: 0, structural (no river-adjacent construction). Land-use conflicts: 0 - station-plaza land acquisition in this window is documented as a cost driver, not as a conflict/dispute; no resistance or grievance is documented, so this stays at 0 for consistency with the Social pathway's own finding of a genuine evidence gap here, rather than inferring a conflict from the acquisition scale alone. Compliance failures: 1 - Department of Environment penalised MRT contractors for air-quality directive violations, 2019 (DMRP_NEWS_016) - the single clearest regulatory enforcement action anywhere in either corpus. | 4
DMRP | 3 | 2022-2024 | 36 | 52.25 | 0 | 0 | 0.5934 | -0.5934 | 0 | 1 | 0 | 0 | 0 | 0.079 | 0.247 | 0.125 | Moderate | Moderate-High | Moderate-High | DMRP_INST_007; DMRP_NEWS_048; DMRP_NEWS_049; DMRP_NEWS_045 | First section (Uttara-Agargaon) actually opened 28 Dec 2022. Dec 2019 -> Dec 2022 = 36 months, confirmed. NOTE: by end of Phase 3 (2024), the second section (Agargaon-Motijheel) had also opened (Nov 2023) - functionally completing the original full-line scope (Uttara-Motijheel, June 2024 target) slightly ahead of that original date. This value tracks only the first-section milestone the manuscript's cited range is based on; it does not capture the separately-scoped, separately-delayed Kamalapur extension (added 2020, now targeting 2027-2028). Flagging for the group: consider whether a second delay variable is needed for the Kamalapur extension specifically, since bundling it into this single figure would conflate two different milestones with two different delay outcomes. | Cost: Tk219.85bn baseline -> Tk334.72bn (Jul 2022 revision) = 52.25% overrun, matching the documented figure exactly. Financing disruption: none documented as a discrete disruption event in this phase (the cost revision itself is captured above, not double-counted here). Contractor claims: none documented. | 0 documented events - this phase is a sequence of station openings and service expansions per Shahriar's evidence pack, with no displacement or interruption content. vader fields blank pending full-text corpus. | Incident density: 1 - the 2023 tree-felling/urban-temperature-rise research finding, though this is an ex-post academic study rather than a regulatory record (a different evidentiary class - see Shahriar's evidence pack note on this exact point). Sedimentation: 0, structural. Land-use conflicts: 0, none documented. Compliance failures: 0, no regulatory action recorded in this phase. | 4
DMRP | 4 | 2024-2026 (interim) | 36 | 48.8 | 1 | 0 | 0.213 | -0.213 | 1 | 1 | 0 | 0 | 0 | 0.407 | 0.75 | 0.125 | Moderate | Moderate | Moderate | DMRP_NEWS_002; DMRP_NEWS_037; DMRP_NEWS_028; DMRP_NEWS_030; DMRP_NEWS_031; DMRP_NEWS_032; DMRP_NEWS_033 | Carried forward unchanged for the first-section milestone this variable tracks. See the Phase 3 note on the separately-tracked Kamalapur extension, which is still actively slipping (now Dec 2028) and is not reflected in this figure. | Cost: Tk219.85bn baseline -> Tk327.17bn (Nov 2025 revision, a cost CUT of Tk755cr from the Phase 3 figure) = 48.8% overrun - a documented DECREASE in overrun percentage from Phase 3's 52.25%, a genuine and reportable finding. Financing disruption: structural revenue shortfall (~Tk4bn fare revenue vs ~Tk7.4bn annual JICA debt service, requiring state subsidy - DMRP_NEWS_037) counted as 1 ongoing disruption event, though this is continuous/structural rather than a discrete incident - flagged as a definitional judgment call. Contractor claims: none documented. | 1 major service-interruption event: the Jul-Aug 2024 arson-driven 37-day network suspension and subsequent station-by-station repair/reopening. Counted as 1 event with sub-components (not 4-5 like the PMBP ferry cluster) because these are stages of a single continuous disruption (one shutdown, one resumption, staged station reopenings) rather than separately-triggered incidents - contrast with the PMBP Phase 3 cluster, which was 9 separately-dated collision/regulatory-response events. Flagging this inconsistency in counting logic between the two clusters for the group to confirm or adjust. vader fields blank pending full-text corpus. | Incident density: 1 - urban space degradation beneath elevated viaducts (informal settlements in cleared walkways, 2024). Sedimentation: 0, structural. Land-use conflicts: 0, none documented. Compliance failures: 0 - deliberately excludes the Oct 2025 structural-safety/no-audit finding (46 piers, 27 bearing pads), since that is a structural-engineering/governance failure, not an EIA/DoE/BIWTA regulatory-compliance failure as this pathway and component are specifically scoped. Recommend routing that evidence to IGQ instead, consistent with the same flag made in the pathway coding file. | 3